🧳 TRAVELOOP

Implementation Plan

Sprint-Based Development Roadmap — Hackathon Edition

# 1. Team Roles

| Role | Responsibilities |
| --- | --- |
| Frontend Lead | React app scaffold, routing, core UI components, state management |
| Backend Lead | Express API, Prisma schema, auth, all endpoints |
| Full Stack Dev | Itinerary builder, budget screen, city/activity search |
| UI/UX | Tailwind styling, responsive layout, component polish |
| QA / DevOps | Testing, deployment, seed data, integration |

# 2. Sprint Plan

## Sprint 0 — Setup (Hours 0–2)

| Task | Owner | Output |
| --- | --- | --- |
| Init React + Vite + TypeScript | Frontend | Working dev server |
| Init Express + Prisma + PostgreSQL | Backend | DB connection verified |
| Define Prisma schema, run migrations | Backend | All tables created |
| Setup Railway/Render deployment | DevOps | CI pipeline active |
| Configure environment variables | All | .env.example committed |
| Seed cities and activities data | Backend | 50+ cities, 200+ activities |

## Sprint 1 — Auth & Core Trip CRUD (Hours 2–6)

| Task | Owner | Output |
| --- | --- | --- |
| Login/Signup UI | Frontend | Auth screens complete |
| POST /auth/login, /auth/signup | Backend | JWT returned |
| Auth middleware + protected routes | Backend | verifyToken working |
| Dashboard screen skeleton | Frontend | Layout + nav |
| GET/POST/DELETE /trips | Backend | Trip CRUD API |
| My Trips screen + Create Trip form | Frontend | Trip list functional |

## Sprint 2 — Itinerary Builder (Hours 6–12)

| Task | Owner | Output |
| --- | --- | --- |
| City search screen + GET /cities | Full Stack | Search working |
| Stop CRUD: POST/PATCH/DELETE /stops | Backend | Stops API |
| Itinerary builder UI + add stop flow | Frontend | Builder screen |
| Activity search screen + GET /activities | Full Stack | Filtered results |
| Stop-activity CRUD endpoints | Backend | Activities linkable |
| Drag-to-reorder stops (dnd-kit) | Frontend | Reorder works |
| Itinerary view screen (list mode) | Frontend | View screen |

## Sprint 3 — Budget, Checklist, Notes (Hours 12–18)

| Task | Owner | Output |
| --- | --- | --- |
| GET /trips/:id/budget (aggregation) | Backend | Cost totals by category |
| Budget screen: charts (Recharts) | Frontend | Pie + bar charts |
| Over-budget alert logic | Full Stack | Red highlight days |
| Checklist CRUD endpoints | Backend | Checklist API |
| Packing checklist screen | Frontend | Functional checklist |
| Notes CRUD endpoints | Backend | Notes API |
| Trip notes screen | Frontend | Add/edit/delete notes |

## Sprint 4 — Share, Profile, Polish (Hours 18–24)

| Task | Owner | Output |
| --- | --- | --- |
| Share token generation + GET /share/:token | Backend | Public URL working |
| Public itinerary view screen | Frontend | Read-only view |
| Social share buttons | Frontend | Copy/WhatsApp/Twitter |
| Profile & settings screen | Frontend | PATCH /users/me |
| Calendar view toggle (itinerary) | Frontend | Calendar layout |
| Responsive mobile pass | UI | 375px+ fully usable |
| Admin dashboard (if time permits) | Full Stack | Stats + tables |

# 3. MVP Priority Matrix

| Feature | Priority | Sprint | Effort |
| --- | --- | --- | --- |
| Auth (login/signup) | P0 Must | 1 | Small |
| Create & manage trips | P0 Must | 1 | Small |
| Add stops + activities | P0 Must | 2 | Medium |
| Itinerary view | P0 Must | 2 | Small |
| City & activity search | P0 Must | 2 | Medium |
| Budget breakdown | P1 Should | 3 | Medium |
| Packing checklist | P1 Should | 3 | Small |
| Trip notes | P1 Should | 3 | Small |
| Share/public URL | P1 Should | 4 | Small |
| Profile & settings | P2 Nice | 4 | Small |
| Calendar view | P2 Nice | 4 | Medium |
| Drag reorder stops | P2 Nice | 2 | Small |
| Admin dashboard | P3 Optional | 4 | Large |

# 4. Risk Register

| Risk | Likelihood | Impact | Mitigation |
| --- | --- | --- | --- |
| DB schema changes mid-sprint | Medium | High | Finalize schema in Sprint 0, use Prisma migrations |
| Time overrun on builder drag-drop | High | Medium | Ship manual reorder first, add dnd as enhancement |
| Cloudinary setup delays | Low | Low | Use local /uploads fallback initially |
| Budget aggregation complexity | Medium | Medium | Pre-calculate on write, cache in trip record |
| Responsive breakpoints | Medium | Medium | Use Tailwind sm: prefix throughout from start |

# 5. Definition of Done

- Feature works end-to-end (frontend → API → DB)

- Mobile-responsive at 375px

- No console errors in browser

- API returns correct status codes (200/201/400/401/404)

- Prisma types match API response shape

- Deployed to staging environment and accessible via public URL